| A. GUIDELINES The SRF makes a distinction between essential changes, which require approval from both parties, and non-essential changes, which do not require formal approval but necessitate a notification from the partner to the FMU. The following changes are classified as essential and require prior approval from the SRF: - Modification of Co-Partner(s): Addition or removal of co-partners. - Financial Modifications: Any financial modification exceeding 10% on any budget chapter heading. - Implementation Period: Changes to the duration of the project. - Report and Payment Conditions: Alterations to the conditions and deadlines for the submission of reports and payment requests. - Objectives, Results, and Indicators: Modifications related to the project's objectives, expected results, and performance indicators. - Beneficiary Changes: - Prior approval is not required when the partner anticipates an increase in the number of beneficiaries, provided this increase does not affect other conditions or elements of the contract with the signing authority. - Conversely, prior approval is required when the partner expects that the number of beneficiaries will not be met. - Country and/or Region of Implementation: Changes to the geographical area of project execution. - Cash and Voucher Modalities: Adjustments to the modalities of cash and voucher assistance. For further information on Modification Requests, please refer to the SRF Operations Manual, which outlines the operational and contractual requirements of the SRF and the procedures to be followed by all parties involved in the implementation of SRF-funded projects. B. PROCESS - The partner must complete this form and submit additional documents to justify the modification request (Updated Proposal, Work Plan, Performance Tracking Matrix, Budget, etc…). - Requests should be submitted as soon as possible and no later than 45 days prior to the project end date. - These changes will be discussed between the FMU and the partner, as per the conditions described in the Operation Manual, and shall be settled within maximum of fifteen (15) days. - No new modification request can be submitted before the previous one is resolved. - the Grantee will complete the Modification Request Template and submit it to reporting@sahelregionalfund.org along with required documents. |  |
| --- | --- |
| SRF Project Information |  |
| Requester’s Name & Job Title: |  |
| Requester’s Email: |  |
| Title of the Project/Identifier Code: |  |
| Date of Revision Request: |  |
| Country (ies) : |  |
| Location(s) and Admin level(s) concerned: |  |
| Project Budget (GBP): |  |
| Estimated Expenditure to date (in month and GBP): |  |
| Original Project End Date: |  |
| Requested Project End Date (NCE only): |  |
| Revision Request Type (check all that apply and fill out the rest of the form accordingly) |  |
| ☐ No-Cost Extension (NCE) request |  |
| ☐ Program Modification request |  |
| ☐ Budget Modification request |  |
| ☐ Contingency Budget |  |
| Please provide a justification for the requested revision with a focus on possible impact on initial targets and performance (500 words). |  |
| I. No-Cost Extension |  |
| - Eligibility Criteria: No-Cost Extensions will only be granted under circumstances where the reasons for the inability to implement all SRF project activities are thoroughly documented. - Maximum Extension Period: The maximum allowable extension period is three months. - Funds Management: If the request for a No-Cost Extension is not approved, all unspent funds must be returned in accordance with the terms outlined in the original Grant Agreement. - Implementation Plan: Please provide a detailed explanation of the specific SRF project activities that will be implemented during the requested extension period. |  |
| Please provide a detailed explanation of the specific SRF project activities that will be implemented during the requested extension period, along with the rationale for these activities. |  |
| [Insert text here] |  |
| II. Program Modification (Submit the proposal in track changes, logframe, work plan, Programme Tracking Matrix, etc..) |  |
| Program Modification is permissible only when accompanied by a clear justification and is required for significant changes in the project scope. - Significant Changes to the Project Scope include, but are not limited to: - An increase in the number of targeted individuals exceeding 15% of the original target. - Changes in the project sector(s). - Major alterations in activities or modalities (e.g., transitioning from Cash and Voucher Assistance (CVA) to in-kind assistance). - Changes in project locations at the ‘admin1’ level. - Minor Changes to the Project Scope (such as changes involving less than 15% in the number of targeted individuals or alterations in project locations at the ‘admin2‘ level) do not require a formal revision request. - All modified activities must be completed prior to the Project End Date, unless a No-Cost Extension has been requested and approved. |  |
| Please describe how the original SRF project activities would be adjusted should the program modification be approved. |  |
| [Insert text here] |  |
| III. Budget Modification (Submit the new budget and other relevant documents) |  |
| Submission Requirements: Any proposed budget modification must include the new revised budget along with all relevant documentation. - Criteria for Budget Modification: - Budget modifications are permissible under well-justified circumstances. - Important changes to the project budget must be necessary to ensure the successful implementation of the SRF project. - Authorization for Budget Variations: - SRF partners are authorized to make budget changes not exceeding 10% of the approved budget for any chapter without prior notification. - Any variations exceeding 10% for a single budget chapter will require prior approval from the Fund Management Unit (FMU). - Creation of Additional Budget Lines: Additional budget lines may be established during the implementation phase, provided that such changes have been communicated to and approved by the FMU. - Modifications may include, but are not limited to: - New activities - Adjustments in budget allocations for specific geographical areas or sectors - Changes to staff or equipment allocations - Expenditure of Modified Funds: All modified funds must be expended prior to the Project End Date, unless a No-Cost Extension is requested and approved at the same time. |  |
| Please share details on the Budget Modification below. |  |
| [Insert text here] |  |
| IV. Contingency Budget (Submit the new budget and other relevant documents) |  |
| Submission Requirements: All submissions must include the following documentation: - Scenario Description: Provide a concise description of the scenario, including: - Locations affected - Number of individuals impacted - Triggers for the intervention - Intervention Strategy and Response Plan: Summarize the proposed intervention strategy and response plan, detailing the overall approach to addressing the situation. - Operational Constraints: Identify and outline key operational constraints that may impact the response efforts. - Revised budget template - Breakdown of Anticipated Costs: Provide an estimate of the anticipated costs associated with the contingency plan. Please ensure to attach a revised budget template depicting planned spending of the contingency budget, including any relevant Bid of Quantities (BoQs) and supporting calculations. - Priority Preparedness Actions: List the priority preparedness actions to be undertaken in anticipation of the situation. - Humanitarian Consequences: Describe the main humanitarian consequences, addressing: - Vulnerabilities and anticipated impacts on affected populations, including the provision of basic services - Coping mechanisms employed by the population - Overall Objectives: Define the overall objectives to be achieved during the response and outline the strategy for accomplishing these objectives. - Collaboration Among Agencies/Organizations: Detail how agencies and organizations will collaborate to ensure a coordinated and effective response to the situation. |  |
| Please provide below the details on Contingency Budget intended utilization. |  |
| [Insert text here] |  |